## Gantt diagram
Weeks
Tasks | 13-19.11 | 20-26.11 | 27.11-03.12 | 04-10.12 | 11-17.12 | 18-24.12 | 25-31.12 | 01-07.01 | 10.01
Research work on basic principles of 3D reconstruction.
Installation of necessary libraries.
Getting familiar with the code and running projects of previus year.
Identification of drawbacks in the programs.
Defining a code improvement strategy.
Theoretical research on point clouds alignment methods
Implementation of alignment methods using OpenCV
Filtering of the registered point cloud before 3D reconstruction
Meshing, hole detection, obtaining color 3D model
Designing GUI
Final test of the code
Preparation of final report and presentation
Defence of the project

## Workflow
Section | Requirement | Status | Implementation status | Testing status
Introduction
| Research work on basic principles of 3D reconstruction. | Done | NA | NA
General requirements
| Installation of necessary libraries. | Done | Done | Done
| configure the privous project and run test | Done | Done | Done
| Getting familiar with the code and running projects of previus year. | Done | NA | NA
| Identification of drawbacks in the programs. | Done | NA | NA
Theoretical research on point clouds alignment methods
| Research work about possibilities using OpenCV | Done | NA | NA
| Reading about feature detection, extraction and matching | Done | NA | NA
Implementation of alignment methods using OpenCV
| Feature detection, extraction, matching using OpenCV | Done | Done | Done
| Implement OpenCV class into the code | In progress
Design of code structure
| Describe and include main classes: | In progress
| Input | In progress
| OpenCV | In progress
| PCL | In progress
Design of GUI
| First draft of future GUI (on paper) | Done | NA | NA
| Include class mainwindow into the code | In progress
| First version of GUI using Qt-Designer | In progress
Filtering of the registered point cloud before 3D reconstruction
Meshing, hole detection, obtaining color 3D model
Final test of the code |  | In Complete |  | Open
Preparation of final report and presentation |  | In Complete |  | Open
|  | In Complete |  | Open
Defence of the project |  | In Complete |  | Open
Open
|  | In Complete |  | Open
Open
|  | In Complete |  | Open
|  | In Complete |  | Open